## Gantt Chart w % Complete
* = an automatically calculated cell
| TASK NAME | START DATE | DAY OF MONTH* | END DATE | DURATION* (WORK DAYS) | DAYS COMPLETE* | DAYS REMAINING* | TEAM MEMBER | PERCENT COMPLETE | WEEK 1 | WEEK 2 | WEEK 3 | WEEK 4
First Sample Project
| Réapprendre Angular, et se connecter avec l'équipe | 2024-07-01 | 1 | 2024-07-08 | 8 | 8 | 0 | Nathan | 100%
| Paramétrer modèle de prix | 2024-07-09 | 9 | 2024-07-11 | 3 | 3 | 0 | Nathan | 100%
| Paramétrer modèle de stockage | 2024-07-10 | 10 | 2024-07-11 | 2 | 2 | 0 | Nathan | 100%
| Paramétrer modèle de suivi | 2024-07-11 | 11 | 2024-07-29 | 19 | 19 | 0 | Nathan | 100%
| Consulter bon de réception | 2024-07-17 | 17 | 2024-07-29 | 13 | 13 | 0 | Nathan | 100%
| Modifier bon de réception | 2024-07-17 | 17 | 2024-08-02 | 17 | 17 | 0 | Nathan | 100%
| Consulter time ligne bon de réception | 2024-07-31 | 31 | 2024-08-02 | 3 | 3 | 0 | Nathan | 100%
| Consulter lignes bons de commande | 2024-07-18 | 18 | 2024-07-29 | 12 | 12 | 0 | Nathan | 100%
| Consulter infos générales bon de réception | 2024-07-19 | 19 | 2024-07-29 | 11 | 11 | 0 | Nathan | 100%
| Affecter lot à bon de réception | 2024-07-23 | 23 | 2024-07-29 | 7 | 7 | 0 | Nathan | 100%
| Créer nouveau lot avec DLC | 2024-07-23 | 23 | 2024-07-29 | 7 | 7 | 0 | Nathan | 100%
| Consulter mouvement de stock | 2024-07-26 | 26 | 2024-08-03 | 9 | 9 | 0 | Nathan | 100%
| Modifier mouvement de stock | 2024-07-26 | 26 | 2024-08-03 | 9 | 9 | 0 | Nathan | 100%
| Consulter time ligne bon de réception | 2024-07-30 | 30 | 2024-08-03 | 5 | 5 | 0 | Nathan | 100%
| Consulter lignes mouvements de stock | 2024-07-27 | 27 | 2024-08-03 | 8 | 8 | 0 | Nathan | 100%
| Consulter infos ligne de mouvement | 2024-07-27 | 27 | 2024-08-03 | 8 | 8 | 0 | Nathan | 100%
| Saisie des emplacements selon type | 2024-07-29 | 29 | 2024-08-03 | 6 | 6 | 0 | Nathan | 100%
| Saisir quantité à expédier | 2024-07-29 | 29 | 2024-08-03 | 6 | 6 | 0 | Nathan | 100%
| Vérifier quantité à expédier | 2024-07-30 | 30 | 2024-08-03 | 5 | 5 | 0 | Nathan | 100%
| Contrôler disponibilité de stock | 2024-07-31 | 31 | 2024-08-03 | 4 | 4 | 0 | Nathan | 100%
| Valider lignes de mouvement de stock | 2024-07-31 | 31 | 2024-08-19 | 20 | 20 | 0 | Nathan | 100%
| Mise à niveau de fiche article | 2024-08-15 | 15 | 2024-08-19 | 5 | 5 | 0 | Nathan | 100%
| Dév. modèles de prix d’article | 2024-08-16 | 16 | 2024-08-19 | 4 | 4 | 0 | Nathan | 100%
| Dév. modèles de dimension de stockage | 2024-08-17 | 17 | 2024-08-19 | 3 | 3 | 0 | Nathan | 100%
| Dév. modèles de dimension de suivi | 2024-08-18 | 18 | 2024-08-26 | 9 | 9 | 0 | Nathan | 100%
| Suppression composante PRICEMODEL | 2024-08-19 | 19 | 2024-08-28 | 10 | 10 | 0 | Nathan | 100%
| Ajout statut VALIDER | 2024-08-26 | 26 | 2024-08-28 | 3 | 3 | 0 | Nathan | 100%
| Gestion statuts DA | 2024-08-27 | 27 | 2024-08-28 | 2 | 2 | 0 | Nathan | 100%
| Bouton passage statut VALIDER | 2024-08-28 | 28 | 2024-08-29 | 2 | 2 | 0 | Nathan | 100%
| Clôture des lignes de DA | 2024-08-29 | 29 |  | #NUM! | #NUM! | #NUM! | Nathan | 100%
Formulas:
DURATION* (WORK DAYS) = DATEDIF([START DATE],[END DATE],"d")+1

## Basic Gantt Chart
| Write Landing Page Copy | 2018-01-05 | 2018-01-08 | 0 | 4 | Nathan | 100%
| Approve Page Copy | 2018-01-08 | 2018-01-11 | 3 | 4 | Meredith | 80%
| Review Landing Page Design | 2018-01-11 | 2018-01-16 | 6 | 6 | Brandon | 60%
| Build Landing Page | 2018-01-14 | 2018-01-19 | 9 | 6 | Michael | 40%
| Code Review Landing Page | 2018-01-17 | 2018-01-23 | 12 | 7 | Rachel | 20%
Second Sample Project
| Write Promotional Email | 2018-01-09 | 2018-01-12 | 4 | 4 | Nathan | 100%
| Design Promotional Email | 2018-01-12 | 2018-01-19 | 7 | 8 | Meredith | 80%
| Send Promotional Email | 2018-01-17 | 2018-01-19 | 12 | 3 | Brandon | 60%
| Analyze Campaign Results | 2018-01-22 | 2018-01-26 | 17 | 5 | Michael | 40%
Third Sample Project
| Plan Agenda for Meeting | 2018-01-15 | 2018-01-19 | 10 | 5 | Nathan | 100%
| Reserve Room | 2018-01-22 | 2018-01-23 | 17 | 2 | Meredith | 80%
| Finalize Presentation | 2018-01-22 | 2018-01-26 | 17 | 5 | Brandon | 60%
| Approve Presentation | 2018-01-26 | 2018-01-29 | 21 | 4 | Michael | 40%
| Create Invitations | 2018-01-22 | 2018-01-25 | 17 | 4 | Rachel | 20%
Fourth Sample Project
| Rewrite Online Calculator | 2018-01-15 | 2018-01-24 | 10 | 10 | Nathan | 100%
| Code Review Calculator | 2018-01-25 | 2018-01-30 | 20 | 6 | Meredith | 80%
| Update Messaging | 2018-01-24 | 2018-01-30 | 19 | 7 | Michael | 60%
| Publish Calculator | 2018-01-30 | 2018-01-31 | 25 | 2 | Rachel | 0%

## Manual Chart
GANTT CHART TEMPLATE
| TASK NAME | START DATE | END DATE | DURATION (WORK DAYS) | TEAM MEMBER | PERCENT COMPLETE | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
[7 empty] | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F
First Sample Project
| Write Landing Page Copy | 2018-01-05 | 2018-01-08 | 2 | Nathan | 100%
|  |  |  | 0 | Meredith | 80% | bar: WEEK 2 M to WEEK 2 T
| Review Landing Page Design | 2018-01-11 | 2018-01-16 | 4 | Brandon | 60% | bar: WEEK 1 F to WEEK 2 Th
| Build Landing Page | 2018-01-14 | 2018-01-19 | 5 | Michael | 40% | bar: WEEK 2 T to WEEK 3 M
| Code Review Landing Page | 2018-01-17 | 2018-01-21 | 3 | Rachel | 20% | bar: WEEK 2 Th to WEEK 3 W
| Promote Landing Page | 2018-01-20 | 2018-01-23 | 2 | Annie | 10% | bar: WEEK 3 T to WEEK 3 Th
Second Sample Project
| Write Promotional Email | 2018-02-05 | 2018-02-08 | 4 | Nathan | 100%
| Design Promotional Email | 2018-02-08 | 2018-02-13 | 4 | Meredith | 80%
| Send Promotional Email to Contacts | 2018-02-11 | 2018-02-16 | 5 | Michael | 60%
| Analyze Results of Email Campagin | 2018-02-14 | 2018-02-23 | 8 | Annie | 40%
Third Sample Project
| Plan Agenda for Team Meeting | 2018-03-05 | 2018-03-08 | 4 | Rachel | 100%
| Reserve Room and Resources for Meeting | 2018-03-08 | 2018-03-13 | 4 | Michael | 80%
| Finalize Team Presentation | 2018-03-11 | 2018-03-16 | 5 | Brandon | 60%
| Review & Approve Presentation | 2018-03-14 | 2018-03-19 | 4 | Meredith | 40%
| Create Invitations for Meeting | 2018-03-17 | 2018-03-21 | 3 | Annie | 20%
| Setup Room for Meeting | 2018-03-20 | 2018-03-25 | 4 | Nathan | 10%
Fourth Sample Project
| Rewrite Code for Online Calculator | 2018-04-05 | 2018-04-08 | 2 | Nathan | 100%
| Code Review Updated Calculator | 2018-04-08 | 2018-04-10 | 2 | Meredith | 80%
| Update Messaging for Calculator | 2018-04-11 | 2018-04-16 | 4 | Michael | 60%
| Publish New Calculator to Site | 2018-04-14 | 2018-04-18 | 3 | Rachel | 40%
Formulas:
DURATION (WORK DAYS) = NETWORKDAYS([START DATE],[END DATE])